## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Student | Register Myself Using Poornima Mail Id | I Can Receive A Confirmation/Verification Mail
1 | SB1/US2 | Student | Receive A Confirmation Mail | I Can Access The Digital College System
1 | SB1/US3 | Student | Login Into The System Using Poornima Mail Id And Password | I Can View/Edit My Profile
1 | SB1/US4 | Student | View The Syllabus | I Can See The Marking Scheme
1 | SB1/US5 | Student | View The Time-Table | I Can Work According To The Time-Table
|  | Student | Modify The Account Password | I Can Keep My Account Secure
|  | Student | Give Feedback/Suggestions | The Way Of Working Of The Department Can Be Improved
|  | Student | Discuss Among Other Students | I Can Share My Experience
|  | Student | View My Indiscipline Activities | I Can Prevent The Mistakes
|  | Student | View My Extra-Curricular Activities | I Can Keep A Check On My Activities
|  | Student | View My Result | I Can Analyze My Performance
|  | Student | View My Attendance | I Can Manage My Attendance
|  | Student | See The Fees Status | I Can Pay The Fees On/Before Time
|  | Student | See The Library+Lab Fine | I Can Pay The Fine On Time
|  | Student | See The Books Issued By Me | I Can Return The Books On Time
|  | Student | See My College Transport Information(If Used) | I Can Have Required Information
|  | Student | View The List Of Celebrations | I Can Participate In The Functions
|  | Student | View The List Of Holidays | I Can Plan My Work
|  | Student | Download Faculty Notes | I Can Be Updated With The Latest Matter Taught In Class
|  | Student | Download Class Assignments | I Can Complete And Submit Them On Time
|  | DBA | Fire Insert Queries | I Can Insert New Records In The Database
|  | DBA | Fire Select Queries | I Can View The Records
|  | DBA | Fire Update Queries | I Can Keep The Database Updated
|  | DBA | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data
|  | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use
|  | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More
|  | HOD | Login Into The System Using Poornima Mail Id And Password | I Can Access The Digital College System
|  | HOD | Modify The Account Password | I Can Keep My Account Secure
|  | HOD | Finalize The Optional Subjects For Current Semester | Course Allotment Can Be Done
|  | HOD | Create Faculty Accounts | Load Allotment Can Be Done
|  | HOD | Allot The Subjects To The Faculties | Time-Table Can Be Made
|  | HOD | View The Time-Table | I Can Monitor The Current Schedule
|  | HOD | Modify The Time Table | The Schedule Can Be Modified Due To Changes
|  | HOD | View The Attendance Of Students | I Can Know The Student Strength In The Department
|  | HOD | View The Attendance Of Students | I Can Know The Faculty Strength In The Department
|  | HOD | View The Debar List | I Can Keep A Check On The Debarred Students
|  | HOD | View The Result List Of The Students | I Can Monitor The Performance Of The Students
|  | HOD | Insert Indiscipline Activities Of Students | I Can Keep A Track Of Discipline
|  | HOD | View Indiscipline Activities Of Students | I Can Give Fair Marking In Discipline Field
|  | HOD | View The List Of Celebrations | I Can Plan Activities For The Celebration
|  | HOD | View The Participation Details Of Activities | Activeness Of The Department Can Be Seen
|  | HOD | Give Bonus Attendance To The Students | Attendance Of Activities Can Be Given To Students
|  | HOD | View Faculty Notes | The Quality Of Notes Can Be Reviewed
|  | HOD | Create Notices | I Can Pass On Important Information
|  | HOD | View Notices | I Can Review Or Read New Notices
|  | HOD | Send Messages To Faculties | They Can Be Informed For An Event
|  | HOD | Send Attendance To Students | They Can Be Informed Their Attendance
|  | HOD | Send Messages To Students | They Can Be Given Important Notices/Updates
|  | HOD | View List Of Eligible Students For Placement | I Can Know The Number Of Eligible Students
|  | Faculty | Login Into The System Using Poornima Mail Id And Password | I Can View/Edit My Profile
|  | Faculty | Modify The Account Password | I Can Keep My Account Secure
|  | Faculty | View The Class Time-Table | I Can Work According To The Time-Table
|  | Faculty | View The Subject Detalis | I Can Work Plan My Lectures
|  | Faculty | Modify The Account Password | I Can Keep My Account Secure
|  | Faculty | View Notices | I Can Review Or Read New Notices
|  | Faculty | Sending Information Through Emails | I Can Send Emails Regarding Important Informations
|  | Faculty | Assign Ppt To Shg | I Can Assign Ppt To The Respective Shg
|  | Faculty | Can View The Details Of Students | I Can Analyze The Academic Details Of Student
|  | Faculty | Give Student Assignment Marks | I Can Give Assignment Marks Of A Subject
|  | Faculty | View Student Attendance In The Subject | I Can View The Attendence Of Studence In My Lecture
|  | Faculty | Assign Spl | I Can Assign Special Lectures For The Particular Topic
|  | Faculty | Upload Video Lectures | I Can Upload Video Lectures
|  | Faculty | View The Progress Of Student | I Can View The Progress Of Students
|  | Faculty | Assign Tutorials To The Shg | I Can Assign Tutorials To The Students And Shg
|  | Faculty | Provide Online Study Material | I Can Provide Study Material Online
|  | Faculty | Taking Online Test | I Can Take Online Tests
|  | Faculty | Upolad Notes | I Can Be Upload The Notes On Time
|  | Faculty | Upload Class Assignments | I Can Upload The Assignment On Time
|  | TPO | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System
|  | TPO | Modify The Account Password | I Can Keep My Account Secure
|  | TPO | Manage The Tpo Activities | I Can Manage Tpo Activities
|  | TPO | Contact To The Industry Representatives | I Can Contact To The Industry Representatives
|  | TPO | Create A List Of Eligible Students | I Can Create A List Of Eligible Students
|  | TPO | Make Announcement Through Email | I Can Make Announcement Through Email
|  | TPO | Create A List Of Active Backlogs In Each Department | I Can Create A List Of Active Backlogs In Each Department
|  | TPO | Sending Information Through Emails | I Can Send Information Through Emails
|  | TPO | Display The Upcoming Company'S Notice | I Can Display The Upcoming Company'S Notice
|  | TPO | Set The Eligibility Criteria Of Peem | I Can Set The Eligibility Criteria Of Peem
|  | TPO | Manage The Time Schedule For Placement Drives | I Can Manage The Time Schedule For Placement Drives
|  | TPO | Select Different Responsibility For Respective Coordinators | I Can Select Manage The Time Schedule For Placement Drives
|  | TPO | View The Details Of All Students | I Can View All The Details Of Students
|  | TPO | Prepare Mock Drives For All Eligible Students | I Can Prepare Mock Drives For All Eligible Students
|  | TPO | Assign Duties To All Placement Coordiantors | I Can Assign Duties To All Placement Coordiantors
|  | TPO | Update Time Table For Placements | I Can Update Time Table Table For Placements
|  | TPO | Access To All Information Of Faculties On Duties | I Can Access The Information Of Faculties On Duties
|  | TPO | Display Total Selections In Comapny | I Can Display Total Selections In Company
|  | TPO | Manage All Statistics And Data About Placements | I Can Manage All Statistics And Data About Placements
|  | TPO | Review And Feedback From Students By Email | I Can Review And Feedback From Students By Email
|  | Transport | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System
|  | Transport | Modify The Account Password | I Can Keep My Account Secure
|  | Transport | Manage The Transport Activities | I Can Manage Transport Activities
|  | Transport | Maintain Data Of All Drivers | I Can Maintain Data Of All Drivers
|  | Transport | Maintain Data Of All Buses | I Can Maintain Data Of All Buses
|  | Transport | Assign Duties To All Drivers | I Can Assign Duties To All Drivers
|  | Transport | Manage The Entries Of Buses As Per Time Schedule | I Can Manage The Entries Of Buses As Per Time Schedule
|  | Transport | Display Contact Details Of Each Driver | I Can Display Contcat Details Of Each Driver
|  | Transport | Provding Id No To The Students To Avail Transport Service | I Can Provide Id No To Students To Avail Transport Service
|  | Transport | Display And Set The Fee Structure As Per Km | I Can Display And Set The Fee Structure As Per Km
|  | Transport | Make Proper Contacts To Update Any Change | I Can Make Proper Contacts To Update Any Change
|  | Transport | Acces To Whole Information About Pickup Points | I Can Access The Details Of All Pickup Points
|  | Transport | Update Time And Place Detail For A Bus | I Can Update Time And Place Detail For A Bus
|  | Transport | Provide Separate Buses For Faculties And Support Staff | I Can Provide Separate Buses For Faculties And Other Staff
|  | Transport | Display The Route Info. For Each Bus | I Can Display The Route Info For Each Bus
|  | Transport | View The List Of Holidays In A Calender Year | View The Details Of Holidays In A Calender Year
|  | Transport | Manage Alternate Route In Case Of Traffic | I Can Manage Alternate Route In Case Of Traffic
|  | Transport | Share Contact Info Of Incharge Of The Campus Transport | I Can Share The Contact Info Of Incharge
|  | Transport | Assign Shift As Per Requirement | I Can Assign Shift As Per Requirement
|  | Transport | Feedback From Students And Faculties | I Can Feedback From Students And Faculties
|  | TUTOR | Maintain The Student Indiscipline Activity Details | I Can Give The Discipline Marks Accordingly
|  | TUTOR | Maintain The Student Extra Curricular Activity Details | I Can Give Bonus Attendance And Marks Accordingly
|  | TUTOR | Contact Parents | I Can Tell Them The Student Performance
|  | TUTOR | View The Debar List | I Can Let Their Parents Know
|  | Timetable CO. | Create New Time Table | Students & Faculty Would Know The Schedule
|  | Timetable CO. | Modify The Time Table | Modification Can Be Done
|  | Timetable CO. | Allocate The Subjects To Faculties | Faculty Will Come To Know What To Teach
|  | Librarian | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System
|  | Librarian | Modify The Account Password | I Can Keep My Account Secure
|  | Librarian | I Want To Insert Book Details | So That Books Information Remain In Database
|  | Librarian | Issue Books | It Is Provided To Students
|  | Librarian | Request To Purchase Books For Library | To Fulfill The Requirements Of Students
|  | Librarian | Request To Purchase Available Resources | To Fulfill The Requirements Of Students
|  | Librarian | Manage The Fine As Per Issued Books | Total Fine Will Be Deducted From Caution Money At The End
|  | Librarian | Make Available Books | To Fulfill The Needs Of Students
|  | Librarian | Makes Available Internet Facility | To Fulfill The Needs Of Students
|  | Librarian | Make Available New Edition Books | Students Are Aware Of Updation In The Book
|  | Librarian | Manage The Copy Of Non-Issue And Issued Books | Books Are Kept Accordingly
|  | Librarian | Manage Novel | Students Get The Knowledge As Per Their Interest
|  | Librarian | Manage Magzines | Students Get The Knowledge As Per Their Interest
|  | Librarian | Manage Old Question Papers Of Midterms And Rtu | Students Get In Touch With The Subject
|  | Librarian | Sms Facility When Due Books | Students Are Aware To Submit The Issued Book On Time
|  | Librarian | Book Availability Alert When A Books Available | Issued Book Is Make Available For Those Who Need It Most
|  | Librarian | New Books ,Magzine, Novel Arrival Alert | Students Get To Know About New Arrivals In Library
|  | Librarian | Book Reference Disk (Cd/Dvd) Content | Students Will Get More Information Related To Subject
|  | Librarian | Manage Entry Of Students | So That Library Record Can Be Maintained
|  | Librarian | Research Paper Management(Content) | So That Students Get Relevant Information
|  | Librarian | Jobs Alert | So That Students Are Aware Of New Job Openings
|  | Librarian | Open Book Test | Students Are Aware About The Topics Of Standard Books
|  | Librarian | Book Review Competition | So That Student Will Put Their Reviews Infront Of Others
|  | Librarian | Project Review Reports Important Samples | It Will Be Available For Students Who Need It Most
|  | Librarian | Manages Different Sections(Reading,Refer,E-Lib) | Easily Available For Everyone As Per Their Need
|  | Librarian | Library Review And Book Review By Users | Share the review with others
|  | Executive | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System
|  | Executive | Modify The Account Password | I Can Keep My Account Secure
|  | Executive | Insert Fee Details | Student Record Related To Fee Is Updated
|  | Executive | Update Hostel Fees | Hostel Irecord Is Up To Date
|  | Executive | Put Fine For Late Fee | Student Are Aware To Submit Fee On Time
|  | Executive | Contact Student | Any Issue Related To Student Is Solved And Informed
|  | Executive | Put Fine For Indiscipline Activity | Indiscipline Activity Are To Be Minimised
|  | Executive | Update The Format Of Fees Receipt | Format Should Be Clear And Conscise
|  | Executive | Contact Director | Overall Activity Report Is Provided To Them
|  | Executive | Monitor Bank Transaction Related To Fee | Fees Updation Procedure Should Be Consistent
|  | Executive | Handle University Exam Form Submission | Exam Fees Are Together Submitted To University
|  | Executive | Handle Transport Fees | Transport Is Make Available To Respective Students
|  | Executive | Handle Money Issues | Supervision Is There
|  | Executive | Manage Technical Staff | Student Contact Directly To Them
|  | Executive | Manage Report As Per Fees To Be Submitted To Head | Director Knows About What Is Happening
|  | Executive | Manage The Faculty Transport Fees | A Specialised Fee For Them
|  | Executive | Manage The Interview Session For New Faculty | New People Get Their Appointment As Per Their Schedule
|  | Executive | Monitor Transport Officer | Transport Related Issues Are To Be Solved
|  | Executive | Manage Salary Of Faculties | The Salary Is Provided To Them On Time
|  | Executive | Manage Salary Of Technical Consultants | The Salary Is Provided To Them On Time
|  | Executive | Manage Convention Centre Booking | Any Competion As Well As Activity Is Conducted
|  | Executive | Manage Task Related To Money | Money Should Be Utilized And Not Wasted
|  | Executive | Monitor Server Control Of College | Lab Work Should Be Flexible And Effective
|  | Director | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System
|  | Director | Modify The Account Password | I Can Keep My Account Secure
|  | Director | Manage The Administration | To Monitor The Effective Supervision
|  | Director | Make Rules | To Assign Equal Responsibility To Everyone
|  | Director | Manage Branches | Workflow Should Be Monitored
|  | Director | Assign Responsibilities To Hod'S,Proctor Etc. | They Will Work According To Their Responsibility
|  | Director | Take Interview Of New Faculties | Faculties With Good Knowledge Will Be Available
|  | Director | Assign Tasks To Campus Director | Hods,Proctor Report To Them And Not Director Everytime
|  | Director | Manage The Placement Activity | Reputed Companies Are Come For Placement
|  | Director | Decide To Allow Activity Conduction As Per Norms | Students Get To Know About Other Things
|  | Director | Monitor Fee Structure | As Per Resources Available Students Get All They Basic Needs
|  | Director | Monitor Teaching As Per Requirement And Rules | Effective Teaching Is Conducted
|  | Director | Monitor Faculty Report And Work | Faculties Are Strict To Follow Norms And Rules
|  | Director | Monitors Admission Norms | Student Admissions Are Increased In College
|  | Director | Impliment Effective Environment All Over | Peaceful Environment And Effective Use Of Resources Are Accomplished
|  | Director | Allow Funding As Per The Resources Need | Resources As Per The Requirement Make Available
|  | Director | Manage Overall Functioning | To Promote Effective And Robust Teaching
|  | Director | Monitors Exam Cell And Their Functioning | Exams Are Conducted In Proper Manner
|  | Director | Monitors The Transport Safety For Day Scholars | Travelling Should Be Safe And Secure
|  | Director | Allow Conference Activity In College | To Promote Knowledge Sharing
|  | Director | Allow Sports Activity As Per Students Need | To Promote Co-Curricular Activities In College
|  | Director | Allow Partnership With Colleges Around | Inter College Activities Are Organized
|  | Director | Monitors And Removes Indicipline Activity In College | Effective Discipline Is Maintained
|  | TA | Login Into The System Using Poornima Mail Id And Password | I Can Login Into The System Using Poornima Mail Id And Password
|  | TA | Modify The Account Password | I Can Keep My Account Secure
|  | TA | Request Complaint Of Students | Students Indiscipined Activity Can Be Recorded
|  | TA | Request For Lab Resources to HOD | The Resources In The Lab Can Be Maintained
|  | TA | View The Requirement Of The Labs | I Can Prepare The Resources
|  | Student | Add Hobbies | I can make my Resume Easily

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Face Recognization System>
SB1/US1 | Collect the image and do the image processing on it | SB1/D1/T1 | 1. Image Acquisition: | PT/IT/PJ | NOT STARTED | End of september
|  | SB1/D1/T2 | 2. Image Enhancement: | PT/IT/PJ | NOT STARTED
|  | SB1/D1/T3 | 3. Image Restoration: | PT/IT/PJ | NOT STARTED
|  | SB1/D1/T4 | 4. Color Image Processing: | PT/IT/PJ | NOT STARTED
|  | SB1/D1/T5 | 5. Wavelets and Multi-Resolution Processing | PT/IT/PJ | NOT STARTED
|  | SB1/D1/T6 | :6. Compression: | PT/IT/PJ | NOT STARTED
SB1/US2 | Collect the image and do the image processing on it | SB1/D2/T1 | 7. Morphological Processing: | PT/IT/PJ | NOT STARTED
|  | SB1/D2/T2 | 8. Segmentation: | PT/IT/PJ | NOT STARTED
|  | SB1/D2/T3 | 9. Representation and Description: | PT/IT/PJ | NOT STARTED
|  | SB1/D2/T4 | 10. Object recognition: | PT/IT/PJ | NOT STARTED
|  | SB1/D2/T5 | 11. Knowledge Base: | PT/IT/PJ | NOT STARTED
SB1/US3 | Implement using python | SB1/D3/T1 | 12 Learn Python | PT/IT/PJ | NOT STARTED
|  | SB1/D3/T2 | 13 Leran Use of Open Cv Library of Python | PT/IT/PJ | NOT STARTED
|  | SB1/D3/T3 | 14.Start Uing Open Cv Library | PT/IT/PJ | NOT STARTED
SB1/D3/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Collect the image and do the image processing on it | Collect Image
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-12 | 30 | 30 | Tasks
2018-09-18 | 0 | 30
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
| Add Department | SB2/D1/T1 | Designing the GUI | SP
|  | SB2/D1/T2 | Connection with database to fetch the data | RA
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TA into the application(using poornima email account) | SB2/D2/T1 | Designing of GUI | PB
|  | SB2/D2/T2 | Validating user input at client level | RM
|  | SB2/D2/T3 | Validating user input at server level | SP
|  | SB2/D2/T4 | Connection with Database to insert the record. | RA
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TA Receiving Confirmation Email | SB2/D3/T1 | Designing of Email(to be send) | PB
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D3/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TO into the application(using poornima email account) | SB2/D4/T1 | Designing of GUI | PB
|  | SB2/D4/T2 | Validating user input at client level | RM
|  | SB2/D4/T3 | Validating user input at server level | SP
|  | SB2/D4/T4 | Connection with Database to insert the record. | RA
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TO Receiving Confirmation Email | SB2/D5/T1 | Designing of Email(to be send) | PB
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D5/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Add Subject | SB2/D6/T1 | Designing of GUI | PB
|  | SB2/D6/T2 | Validating user input at client level | RM
|  | SB2/D6/T3 | Validating user input at server level | SP
|  | SB2/D6/T4 | Connection with Database to insert the record. | RA
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register Timetable Co-ordinator into the application | SB2/D7/T1 | Designing of GUI | PB
|  | SB2/D7/T2 | Validating user input at client level | RM
|  | SB2/D7/T3 | Validating user input at server level | SP
|  | SB2/D7/T4 | Connection with Database to insert the record. | RA
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Timetable Co-ordinator Receiving Confirmation Email | SB2/D8/T1 | Designing of Email(to be send) | PB
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D8/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days